## Instructions
For each row on the Risk tab:
Are the description and impact clear?
Is the list of Current Mitigations accurate?
Can you think of other Possible Mitigations (whether or not you currently intend to implement them?)
Set values for Impact Level and Likelihood.
If any actions are already planned for a given risk, add them to Initiatives.
Add more rows for risks specific to your business and populate them.
After you have all the rows, then:
Set the values for impact and likelihood for each row.
Set the Treatment column to the most appropriate value.
Sort the sheet by risk score.
Review the sheet with company leadership periodically.

## Risk
Risk ID | Category | Risk | Description | Potential Impact | Likelihood | Severity | Impact Score | Likelihood Score | Risk Level | Possible Mitigations | Treatment | Notes
RSK-039 | Cloud & SaaS | Shadow IT | Employees adopt unapproved SaaS tools (file-sharing, GenAI, productivity apps) outside official controls. | * Data stored in uncontrolled locations * Compliance violations * Increased attack surface | High | High | 4 | 4 | 16 | * Educate staff * Publish list of approved tools * Use SSO to limit access to sanctioned apps
RSK-038 | Identity & Access | Weak Authentication | Lack of multi-factor authentication (MFA) or inconsistent enforcement across systems. | * Account compromise * Unauthorized access to sensitive systems * Business disruption | High | Very High | 5 | 4 | 20 | * Enforce MFA on all business accounts * Disable legacy authentication * Monitor for non-compliant accounts.
RSK-037 | Operations & Resilience | Patch & Update Gaps | Failure to apply operating system, application, or device patches in a timely manner. | * Exploitation of known vulnerabilities * Malware/ransomware infection * Regulatory or contractual noncompliance | High | Very High | 5 | 4 | 20 | * Enable automatic updates where possible * Schedule patch cyclestrack and verify patch status
RSK-036 | Cloud & SaaS | Over-Privileged SaaS Integrations | Third-party SaaS integrations (e.g., CRM add-ons, automation tools) granted excessive permissions. | * Data exfiltration if integration is compromised * Lateral movement into core systems | Moderate | High | 4 | 3 | 12 | * Review app permissions before approval * Use least-privilege access * Audit integrations regularly
RSK-035 | Physical & Environmental | Natural Disaster | An earthquake or storm could damage the AWS zone where all our servers and data are hosted. | * Loss of AWS resources--servers, backups, buckets, etc. * Loss of data * Business operations halted | Low | High | 4 | 2 | 8 | * Purchase AWS resources in an alternate zone for backup and redundancy * Use physical media to store backups somewhere secure
RSK-034 | Operations & Resilience | Monitoring & Logging Gaps | Lack of central logging or monitoring makes security incidents go undetected. | * Extended attacker dwell time * Larger breaches before discovery * Increased regulatory/insurance exposure | Moderate | High | 4 | 3 | 12 | * Enable logging on critical systems * Use centralized log collection * Review alerts regularly
RSK-033 | Human Factors | Inadequate Security Expertise | Organization lacks in-house security knowledge to assess risks, configure controls, or evaluate vendors effectively. | * Misconfigured systems and controls * Inability to detect/respond to incidents * Poor vendor or contract decisions * Elevated residual risk across all areas | Moderate | High | 4 | 3 | 12 | * Engage external advisors or MSPs * Provide role-appropriate training * Adopt lightweight frameworks for structure
RSK-032 | Human Factors | Email & Collaboration Tool Misuse | Sensitive data shared insecurely via email, chat, or file-sharing platforms without safeguards. | * Accidental data exposure * Loss of customer trust * Regulatory fines | Moderate | High | 4 | 3 | 12 | * Provide secure file-sharing alternatives * Train staff on safe use of collaboration tools * Monitor outbound sharing
RSK-031 | Operations & Resilience | Unverified Backups & Recovery | Backups exist but are not regularly tested or isolated. Recovery after ransomware or outage may fail. | * Extended downtime * Permanent data loss * Business disruption | Moderate | Very High | 5 | 3 | 15 | * Test backups regularly * Keep offline/immutable copies * Include recovery in continuity planning
RSK-030 | Data Management | Poor Data Retention & Shadow Data | Sensitive data retained longer than necessary or stored in uncontrolled locations (personal devices, unapproved apps). | * Regulatory fines * Increased breach impact * Harder to secure and manage | Moderate | High | 4 | 3 | 12 | Define retention rules * Regularly clean up old data * Educate staff to avoid unapproved storage.
RSK-029 | Fraud | Business Email Compromise | Attackers impersonate executives or vendors via email to trick staff into transferring money or sensitive data. | * Financial loss * Legal liability * Customer/vendor relationship damage | Moderate | Very High | 5 | 3 | 15 | * Train staff on BEC * Implement payment verification procedures * Enable email authentication (DMARC, SPF, DKIM)
RSK-028 | Operations & Resilience | Pandemic/Disaster | A pandemic or natural disaster could make unavailable portions of our staff (or vendor/partner staff.) | * Reduced productivity * Customer service delays * Supply chain disruptions | Low | Low | 2 | 2 | 4 | * Document key tasks and train backup personnel
RSK-027 | Regulations | Regulatory compliance drift | New regulations, or changes to existing regulations such as GDPR, could affect <company> | * Compliance failure * Chance of increased regulatory fines * Increased compliance cost * Loss of customer trust | Moderate | Low | 2 | 3 | 6 | * Subscribe to regulatory update services * Engage with industry associations and compliance communities * Arrange compliance reviews with external experts * Establish relationships with specialized healthcare attorneys
RSK-026 | Human Factors | Remote work security gaps | Home network vulnerabilities, family members accessing work devices, unsecured video calls discussing sensitive matters. | * Data exposure from accessible - internal systems - cloud platform | Moderate | High | 4 | 3 | 12 | * Train users on safe home usage * Systematically audit laptops for evidence of shared usage. * Require dedicated workspaces with physical controls * Inspect home office environments for suitability (could be done by webcam.) * Create home office secuirty checklists and require periodic self-assessment
RSK-025 | Endpoints & Devices | Compromised network connection | Data transmitted could be intercepted if not properly encrypted. | * Data exposure from accessible - internal systems - cloud platform | Moderate | High | 4 | 3 | 12 | * Train users to consider reliability of unknown wifi providers. * Train users to manage home routers safely. * Require VPN for connecting to secure systems. * Provide staff with company-issued phones that provide hotspots. * Use encrypted protocols such as HTTPS for all connections
RSK-024 | Identity & Access | Privilege creep | A staff member may be granted access permissions over time and, particularly when changing roles, gradually accumulate more privileges than needed for the current role. | * Increased exposure if the privilege user's credentials are hacked * Increased potential for more damaging insider attack | High | Moderate | 3 | 4 | 12 | * Establish standard workflow(s) with approval(s) for granting access privileges to anyone * When users change roles, always review existing privileges to see what can be removed. (RBAC facilitates this: delete all existing access privileges and then assign those RBAC roles associated with the user's new position.
RSK-023 | Identity & Access | Unapproved access | A staff member may be granted new access permissions without a legitimate business need, violating the principle of least privilege. | * Increased exposure if the privilege user's credentials are hacked * Increased potential for more damaging insider attack | Moderate | Moderate | 3 | 3 | 9 | * Establish standard workflow(s) with approval(s) for granting access privileges to anyone * Ensure that no request is granted without adequate confirmation that it meets a legitimate business need. * Ensure that all access requests and grants are logged immutably.
RSK-022 | Human Factors | Untrained staff | A staff member who has not received company training but has been granted access to sensitive data may handle the data improperly, inadvertently creating a security incident. | * Data exposure from accessible - internal systems - cloud platform - customer systems (ePHI) * Compliance failure * Increased legal and regulatory liability | Moderate | Moderate | 3 | 3 | 9 | * Establish standard workflow(s) with approval(s) for granting access privileges to anyone * Confirm that training has been delivered and acknowledged before approving any request for access to sensitive systems.
RSK-021 | Endpoints & Devices | Virus on user device | Malware installed on user device (via phishing, downloaded file, etc.) This could result in a hacker having extended unauthorized access to accessible IT systems. | * Malicious actor access to systems * Legal liability accumulation * Disruption of accessible IT systems * Ransomware spread to accessible systems | Low | High | 4 | 2 | 8 | * Choose industry-standard anti-virus * Use multiple malware detectors * Use MDM to require that a/v software update regularly * Monitor MDM to ensure a/v is updating regularly * Monitor laptops centrally for signs of anomalous behavior
RSK-020 | Vendors & Supply Chain | Vendor breach | Third-party SaaS vendor suffers a breach | * Data exfiltration from business and/or production systems * Employee productivity loss * Disruption of services to customers * Damage to brand * Increased vulnerability to other attacks | Moderate | Moderate | 3 | 3 | 9 | * Institute a vendor management program * Assess the risks in, and security capabilities of, potential new vendors * Do not sign vendor contracts until the results of the risk assessment is known and accepted * Periodically review the risks and security capabilities of each existing vendor
RSK-019 | Operations & Resilience | Security program lapses | Security commitments in our Security Working Agreement may be executed only partially or inconsistently, perhaps increasingly so over time, weakening the overall security posture. | * Increased vulnarability to other attacks * Compliance fault * Regulatory fines | Moderate | High | 4 | 3 | 12 | * Require periodic audit of controls to confirm they are functioning correctly. * Include employee sanctions in staff training * Include security responsibilities in job descriptions * Demonstrate consistent executive support for the security program * Require employees to agree to security policies as a condition of employment
RSK-018 | Operations & Resilience | Mishandling of security incidents | Failure to diagnose a problem correctly; erroneous or ineffective measures to remove risk and restore systems; failure to observe contractual and regulatory obligations concerning affected users; failure to find the root cause and address newly discovered risk. | * Inadvertently increase scope of data exposure * Increase regulatory fines * Violate regulatory or contractual obligations | Moderate | High | 4 | 3 | 12 | * Ensure the incident response plan is comprehensive and clear * Train likely participants in IR processes * Practice the IR process annually, perhaps with a table-top exercise * Include employee sanctions in staff training
RSK-017 | Cloud & SaaS | Cloud Service Misconfiguration | Accidental public exposure of files, buckets, or SaaS data due to weak sharing settings. | * Unauthorized data access * Compliance breach * Customer trust loss | Moderate | Very High | 5 | 3 | 15 | * Restrict sharing defaults * Monitor access logs * Periodic configuration review
RSK-016 | Operations & Resilience | Delay discovering compromise | <company> systems may be compromised and the breach discovered only much later. | * Ongoing data exposure * Business disruption, including ransomware * Legal liability accumulation * Damage to brand | Moderate | High | 4 | 3 | 12 | * Document required logging goals and events * Create alerts for anomalous events * Consider Microsoft Defender for Endpoints to get more configurable alerts than Intune provides * Create custom alert rules related to <company>-specific activity
RSK-015 | Endpoints & Devices | User device damaged or destroyed | Laptop is damaged or destroyed due to environmental hazard. | * Equipment loss * Business disruption * Employee productivity loss | Very Low | Very Low | 1 | 1 | 1 | * Require users to store laptops only in safe locations. * Provide authorized mechanisms for users to back up machines or keep remote copies (to minimize disruption) * Maintain a stock of extra laptops (to minimize disruption) * Insure laptops (to reduce cost)
RSK-014 | Identity & Access | Rogue sysadmin | Insider (staff) with admin priviliges executes a careful slow attack. | * Business disruption (including ransomware) * Data exfiltration from accessible - internal systems - cloud platform - customer systems (ePHI) * Regulatory fines * Damage to brand | Low | Very High | 5 | 2 | 10 | * Enforce separation of duties * Send all automated alerts to at least two addresses * Collect logs in centralized locations (Such as Defender for endpoints or Log Analytics for Azure) * Require approval from, or participation of, a second person for critical admin actions (approval workflow) * Avoid "standing privileges" using Just in Time (JIT) access or break-glass accounts
RSK-013 | Remote Work | Unsecured Remote / BYOD Use | Staff working remotely or on personal devices without endpoint protection or secure connections. | * Data leakage * Device compromise spreads to company systems * Regulatory exposure | High | High | 4 | 4 | 16 | * Require device management or endpoint protection * VPN or secure access * Clear BYOD policies
RSK-012 | Identity & Access | Compromised employee credentials | Malicious actor gets credentials to a <company> account. | * Unauthorized access to office systems * Data exfiltration from customer systems * Disruption of customer systems * Compliance investigation costs * Regulatory fines * Damage to brand | Moderate | Very High | 5 | 3 | 15 | * Require MFA for all Azure AD logins * Enforce good password policies * Train users on protecting passwords
RSK-011 | Identity & Access | Angry ex-employee | Offboarded employee retains access to SaaS tools or customer data | * Business disruption (including ransomware) * Data exfiltration from accessible - internal systems - cloud platform - customer systems (ePHI) * Compliance investigation costs * Legal costs * Regulatory fines * Damage to brand | Low | High | 4 | 2 | 8 | * Formalize an offboarding checklist * Require that enterprise credentials be cancelled as close as practical to the moment employees leave * Train staff to recognize and report potential insider threat
RSK-010 | Human Factors | Social engineering attack | Social engineering leads to unauthorized system access and info leakage. | * Business disruption (including ransomware) * Data exfiltration from accessible - internal systems - cloud platform - customer systems (eHI) * Regulatory fines * Damage to brand | Moderate | Very High | 5 | 3 | 15 | * Train staff to recognize and resist social engineering * Ensure laptop anti-virus is always running and updating regularly * Do not give users admin access to their laptops
RSK-009 | Human Factors | Sharing data insecurely | Employees share sensitive data in inappropriate or unauthorized channels | * Data disclosed to unauthorized personnel * Data disclosed externally if a malicious actor acquires access to company systems * Compliance failure | High | Low | 2 | 4 | 8 | * Prohibit by policy sharing ePHI in unauthorized channels * Train staff not to share in unauthorized channels * Train staff how to respond if data is shared in unauthorized channels * Monitor unauthorized channels periodically for violations * Create, purchase, or configure automatic monitoring to alert if ePHI appears in unauthorized channels * Include employee sanctions in staff training
RSK-008 | Human Factors | Poor Policy & Awareness | Staff unaware of expectations around passwords, devices, or remote work. No written policies to set boundaries. | * Inconsistent practices * Preventable mistakes * Elevated risk of breaches | Moderate | High | 4 | 3 | 12 | * Publish short clear policies * Provide annual security awareness training * Reinforce via onboarding
RSK-007 | Endpoints & Devices | User device lost or stolen | A device used for <company> work is misplaced, left behind, or stolen. | * Equipment loss * Employee productivity loss * Potential data exfiltration from <company> systems * Potential <company> system disruption | Low | Low | 2 | 2 | 4 | * Train staff to protect laptops * Provide users with laptop locks
RSK-006 | Endpoints & Devices | MDM enrollment failure | Laptop is not properly enrolled in MDM (e.g., Intune), and is not manageable. Results in security control lapses that could be exploited by a malicious threat actor. | * Business disruption * Data exfiltration from accessible - internal systems - cloud platform - customer systems (ePHI) * Compliance fault * Regulatory fines * Damage to brand | Moderate | High | 4 | 3 | 12 | * Use a checklist for enrolling in MDM. Finish by confirming correct enrollment. * Monitor laptops regularly for continued enrollment.
RSK-005 | Endpoints & Devices | Hacked laptop | Remote attacker gains access to an <company> user device via RDP or other remote access software. | * Unauthorized access to all data on device * Attack may escalate to other devices/systems * Data exfiltration and/or system disruption * Compliance investigation costs * Regulatory fines * Damage to brand | Moderate | Very High | 5 | 3 | 15 | * Train staff on social engineering * Require staff not to let anyone else use their laptop * Maintain up-to-date antivirus on laptops * Establish alerts (InTune) for suspicious activity * Actively monitor activity * Do not give users admin access to their laptops
RSK-004 | Endpoints & Devices | Confidential or Restricted data on laptops | Sensitive data is cached or stored locally. Could be exploited by a threat actor who steals or compromises the laptop. | * Exfiltration of ePHI * Compliance fault | High | Moderate | 3 | 4 | 12 | * Prohibit by policy copying ePHI * Train staff not to copy ePHI * Disable copying ePHI where possible * Monitor laptops periodically to ensure staff are not making local copies * Monitor company comm channels to ensure staff are not sharing ePHI
RSK-003 | Endpoints & Devices | Compromised customer credentials | Attacker acquires credentials to a customer account in our product (phishing, social engineering…) | * Data exfiltration from customer systems * Loss of trust (if our system is perceived to be attackable) | Low | Very High | 5 | 2 | 10 | * Require password hygiene in policies * Train staff on password hygiene * Encourage or require use of a password manager * Ensure customer requires MFA for access
RSK-002 | Vendors & Supply Chain | Weak Vendor Oversight | Third-party services adopted without security or compliance checks. Vendors may add features (e.g., AI, analytics) without notice. | * Data exposure * Regulatory noncompliance * Service disruption | Moderate | High | 4 | 3 | 12 | * Lightweight vendor questionnaire * Include security/AI clauses in contracts * Review vendors periodically
RSK-001 | Cloud & SaaS | Office systems go down | SaaS provider outage disrupts <company> access to office systems (Office 365, Slack, GitHub, etc.) | * Business disruption * Employee productivity loss * Customer service delays * Revenue loss during outage * Damage to brand if prolonged | Very Low | Moderate | 3 | 1 | 3 | * Include SLAs when evaluating vendors * Establish alternate comm channels for staff

## Risk Levels
Likelihood | Description | Practical Indicators
Very High | Expected to occur repeatedly (e.g., monthly or more). No controls or easy to exploit. | Happens frequently across the industry or internally. Example: automated login attacks, unpatched CVEs.
High | Likely to occur at least once per year. Common and credible threat. | Phishing, credential stuffing, minor misconfigurations.
Medium | Possible but not frequent. Could occur under certain conditions. | Insider mishandling, single-point supplier outage.
Low | Unlikely, but plausible under exceptional conditions. | Major ISP outage, targeted attack on a small firm.
Very Low | Extremely rare or hypothetical. Requires extraordinary circumstances. | Natural disasters, global pandemics.
Severity | Description | Observable Consequences
Very High | Severe, business-threatening loss or extended outage. | Customer exodus, major data breach, executive/legal crisis.
High | Major disruption or loss, but survivable with significant cost. | Days of downtime, serious data loss, regulator or media attention.
Medium | Noticeable impact requiring management action and recovery effort. | Partial service outage, moderate financial loss, some customer impact.
Low | Minor inconvenience with little or no customer effect. | Brief downtime, small internal cost, no external reporting.
Very Low | Negligible impact, quickly reversible. | Momentary glitch, easily restored file.

## Risk Scores
Likelihood
|  | 1 | 2 | 3 | 4 | 5
Severity | 1 | 1 | 2 | 3 | 4 | 5
| 2 | 2 | 4 | 6 | 8 | 10
| 3 | 3 | 6 | 9 | 12 | 15
| 4 | 4 | 8 | 12 | 16 | 20
| 5 | 5 | 10 | 15 | 20 | 25

## Internals
Risk Treatments | Levels | Categories
Accept | Very High
Avoid | High
Reduce | Moderate
Transfer | Low
Very Low

## License
Sample risk register provided by SafetyLight LLC.
Released under CC0 1.0 Universal (Public Domain Dedication).
Provided as-is; customize for your organization.
The original document is on GitHub:
https://github.com/SafetyLight/Presentations/tree/main/Minimum%20Viable%20Security%20Program